## Active WorkPlan
| Week Number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
| Precentage Completiton | 2.941% | 5.882% | 8.824% | 11.76% | 14.71% | 17.65% | 20.59% | 23.53% | 26.47% | 29.41% | 32.35% | 35.29% | 38.24% | 41.18% | 44.12% | 47.06% | 50% | 52.94% | 55.88% | 58.82% | 61.76% | 64.71% | 67.65% | 70.59% | 73.53% | 76.47% | 79.41% | 82.35% | 85.29% | 88.24% | 91.18% | 94.12% | 97.06% | 100%
| Label | 1: Start of Autumn Semester; 3: 12th October Project Proposal - Soft; 5: 22nd October Project Proposal - 0% Preliminary Ethics Check; 11: 7th December Interim Report - 10%; 19: Start of Spring Semester; 29: 12th April Research Paper - 75%; 34: 16/17th May Presentation - 15%
Code | Week | 2018-09-24 | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24 | 2018-12-31 | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13
Documentation
D1 | Project Proposal Draft | bar: 2018-10-08
D2 | Project Proposal Finalise | bar: 2018-10-15 to 2018-10-22
D3 | Preliminary Ethics Checklist | bar: 2018-10-15
D4 | Interim Report Outline Sections | bar: 2018-11-19
D5 | Interim Report Related Work | bar: 2018-11-05 to 2018-11-19
D6 | Interim Report Draft | bar: 2018-11-19 to 2018-11-26
D7 | Interim Report Finalise | bar: 2018-12-03
D8 | Research Paper Structure Sections | bar: 2019-03-11
D9 | Research Paper Abstract | bar: 2019-03-11 to 2019-03-18
D10 | Research Paper Draft | bar: 2019-03-18 to 2019-04-01
D11 | Research Paper Video Demo | bar: 2019-04-08
D12 | Research Paper Finalise | bar: 2019-04-08
Research
R1 | Background Research | bar: 2018-10-01 to 2018-10-15
R2 | GVGAI Basic Research | bar: 2018-10-22 to 2018-10-29
R3 | GVGAI Framework Review | bar: 2018-10-29 to 2018-11-05
R4 | GVGAI Papers for Related Works | bar: 2018-10-29 to 2018-11-12
R5 | Other Related Works | bar: 2018-11-12 to 2018-11-19
R6 | Research for Solution | bar: 2018-12-17 to 2019-03-04
Development
S1 | Install GVGAI Framework | bar: 2018-10-22 to 2018-10-29
S2 | Implement Random Agent | bar: 2018-10-29 to 2018-11-05
S3 | Run avalible Previous Agents | bar: 2018-10-29 to 2018-11-12
S4 | Develop Solution | bar: 2018-12-17 to 2019-03-04
Presentation
P1 | Presentation General Outline | bar: 2019-04-29 to 2019-05-06
P2 | Create Demo for Presentation | bar: 2019-04-29 to 2019-05-06
P3 | Finalise Presentation | bar: 2019-05-13
P4 | Present Presentation | bar: 2019-05-13
Miscellaneous
M1 | Create Git repository | bar: 2018-10-01
M2 | Install LaTeX | bar: 2018-10-01
M3 | Create Meeting Minutes Document | bar: 2018-10-22
M4 | Plan 2nd stage of Project | bar: 2018-12-10
M5 | Print and Collate Final Hand In | bar: 2019-04-08
M6 | SET/SEM Questionaries | bar: 2019-05-13
Other Commitments
C1 | Welcome Weeks | bar: 2018-09-24 to 2018-10-01
C2 | Christmas Holiday | bar: 2018-12-17 to 2019-01-07
C3 | Autumn Exams | bar: 2019-01-14 to 2019-01-21
C4 | Easter Holiday | bar: 2019-04-15 to 2019-05-06

## Project Proposal
| Week Number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
| Precentage Completiton | 2.941% | 5.882% | 8.824% | 11.76% | 14.71% | 17.65% | 20.59% | 23.53% | 26.47% | 29.41% | 32.35% | 35.29% | 38.24% | 41.18% | 44.12% | 47.06% | 50% | 52.94% | 55.88% | 58.82% | 61.76% | 64.71% | 67.65% | 70.59% | 73.53% | 76.47% | 79.41% | 82.35% | 85.29% | 88.24% | 91.18% | 94.12% | 97.06% | 100%
| Label | 1: Start of Autumn Semester; 3: 12th October Project Proposal - Soft; 5: 22nd October Project Proposal - 0% Preliminary Ethics Check; 11: 7th December Interim Report - 10%; 19: Start of Spring Semester; 29: 12th April Research Paper - 75%; 34: 16/17th May Presentation - 15%
Code | Week | 2018-09-24 | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24 | 2018-12-31 | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13
Documentation
D1 | Project Proposal Draft | bar: 2018-10-08
D2 | Project Proposal Finalise | bar: 2018-10-15 to 2018-10-22
D3 | Preliminary Ethics Checklist | bar: 2018-10-15
D4 | Interim Report Outline Sections | bar: 2018-11-19
D5 | Interim Report Related Work | bar: 2018-11-05 to 2018-11-19
D6 | Interim Report Draft | bar: 2018-11-19 to 2018-11-26
D7 | Interim Report Finalise | bar: 2018-12-03
D8 | Research Paper Structure Sections | bar: 2019-03-11
D9 | Research Paper Abstract | bar: 2019-03-11 to 2019-03-18
D10 | Research Paper Draft | bar: 2019-03-18 to 2019-04-01
D11 | Research Paper Video Demo | bar: 2019-04-08
D12 | Research Paper Finalise | bar: 2019-04-08
Research
R1 | Background Research | bar: 2018-10-01 to 2018-10-15
R2 | GVGAI Basic Research | bar: 2018-10-22 to 2018-10-29
R3 | GVGAI Framework Review | bar: 2018-10-29 to 2018-11-05
R4 | GVGAI Papers for Related Works | bar: 2018-10-29 to 2018-11-12
R5 | Other Related Works | bar: 2018-11-12 to 2018-11-19
R6 | Research for Solution | bar: 2018-12-17 to 2019-03-04
Development
S1 | Install GVGAI Framework | bar: 2018-10-22 to 2018-10-29
S2 | Implement Random Agent | bar: 2018-10-29 to 2018-11-05
S3 | Run avalible Previous Agents | bar: 2018-10-29 to 2018-11-12
S4 | Develop Solution | bar: 2018-12-17 to 2019-03-04
Presentation
P1 | Presentation General Outline | bar: 2019-04-29 to 2019-05-06
P2 | Create Demo for Presentation | bar: 2019-04-29 to 2019-05-06
P3 | Finalise Presentation | bar: 2019-05-13
P4 | Present Presentation | bar: 2019-05-13
Miscellaneous
M1 | Create Git repository | bar: 2018-10-01
M2 | Install LaTeX | bar: 2018-10-01
M3 | Create Meeting Minutes Document | bar: 2018-10-22
M4 | Plan 2nd stage of Project | bar: 2018-12-10
M5 | Print and Collate Final Hand In | bar: 2019-04-08
M6 | SET/SEM Questionaries | bar: 2019-05-13
Other Commitments
C1 | Welcome Weeks | bar: 2018-09-24 to 2018-10-01
C2 | Christmas Holiday | bar: 2018-12-17 to 2019-01-07
C3 | Autumn Exams | bar: 2019-01-14 to 2019-01-21
C4 | Easter Holiday | bar: 2019-04-15 to 2019-05-06

## Project Proposal (Print)
| Week Number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
| Percentage Completion | 2.941% | 5.882% | 8.824% | 11.76% | 14.71% | 17.65% | 20.59% | 23.53% | 26.47% | 29.41% | 32.35% | 35.29% | 38.24% | 41.18% | 44.12% | 47.06% | 50% | 52.94% | 55.88% | 58.82% | 61.76% | 64.71% | 67.65% | 70.59% | 73.53% | 76.47% | 79.41% | 82.35% | 85.29% | 88.24% | 91.18% | 94.12% | 97.06% | 100%
| Label | 1: Start of Autumn Semester; 3: 12th October Project Proposal - Soft; 5: 22nd October Project Proposal - 0% Preliminary Ethics Check; 11: 7th December Interim Report - 10%
Code | Week | 2018-09-24 | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24 | 2018-12-31 | 2019-01-07 | 2019-01-14 | 2019-01-21
Documentation
D1 | Project Proposal Draft | bar: 2018-10-08
D2 | Project Proposal Finalise | bar: 2018-10-15 to 2018-10-22
D3 | Preliminary Ethics Checklist | bar: 2018-10-15
D4 | Interim Report Outline Sections | bar: 2018-11-19
D5 | Interim Report Related Work | bar: 2018-11-05 to 2018-11-19
D6 | Interim Report Draft | bar: 2018-11-19 to 2018-11-26
D7 | Interim Report Finalise | bar: 2018-12-03
D8 | Research Paper Structure Sections
D9 | Research Paper Abstract
D10 | Research Paper Draft
D11 | Research Paper Video Demo
D12 | Research Paper Finalise
Research
R1 | Background Research | bar: 2018-10-01 to 2018-10-15
R2 | GVGAI Basic Research | bar: 2018-10-22 to 2018-10-29
R3 | GVGAI Framework Review | bar: 2018-10-29 to 2018-11-05
R4 | GVGAI Papers for Related Works | bar: 2018-10-29 to 2018-11-12
R5 | Other Related Works | bar: 2018-11-12 to 2018-11-19
R6 | Research for Solution | bar: 2018-12-17 to 2019-01-21
Development
S1 | Install GVGAI Framework | bar: 2018-10-22 to 2018-10-29
S2 | Implement Random Agent | bar: 2018-10-29 to 2018-11-05
S3 | Run available Previous Agents | bar: 2018-10-29 to 2018-11-12
S4 | Develop Solution | bar: 2018-12-17 to 2019-01-21
Presentation
P1 | Presentation General Outline
P2 | Create Demo for Presentation
P3 | Finalise Presentation
P4 | Present Presentation
Miscellaneous
M1 | Create Git repository | bar: 2018-10-01
M2 | Install LaTeX | bar: 2018-10-01
M3 | Create Meeting Minutes Document | bar: 2018-10-22
M4 | Plan 2nd stage of Project | bar: 2018-12-10
M5 | Print and Collate Final Hand In
M6 | SET/SEM Questionaries'
Other Commitments
C1 | Welcome Weeks | bar: 2018-09-24 to 2018-10-01
C2 | Christmas Holiday | bar: 2018-12-17 to 2019-01-07
C3 | Autumn Exams | bar: 2019-01-14 to 2019-01-21
C4 | Easter Holiday
| Label | 2018-09-24: Start of Spring Semester; 2018-12-03: 12th April Research Paper - 75%; 2019-01-07: 16/17th May Presentation - 15%
Code | Week | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13
Documentation
D1 | Project Proposal Draft
D2 | Project Proposal Finalise
D3 | Preliminary Ethics Checklist
D4 | Interim Report Outline Sections
D5 | Interim Report Related Work
D6 | Interim Report Draft
D7 | Interim Report Finalise
D8 | Research Paper Structure Sections | bar: 2019-03-11
D9 | Research Paper Abstract | bar: 2019-03-11 to 2019-03-18
D10 | Research Paper Draft | bar: 2019-03-18 to 2019-04-01
D11 | Research Paper Video Demo | bar: 2019-04-08
D12 | Research Paper Finalise | bar: 2019-04-08
Research
R1 | Background Research
R2 | GVGAI Basic Research
R3 | GVGAI Framework Review
R4 | GVGAI Papers for Related Works
R5 | Other Related Works
R6 | Research for Solution | bar: 2019-01-28 to 2019-03-04
Development
S1 | Install GVGAI Framework
S2 | Implement Random Agent
S3 | Run available Previous Agents
S4 | Develop Solution | bar: 2019-01-28 to 2019-03-04
Presentation
P1 | Presentation General Outline | bar: 2019-04-29 to 2019-05-06
P2 | Create Demo for Presentation | bar: 2019-04-29 to 2019-05-06
P3 | Finalise Presentation | bar: 2019-05-13
P4 | Present Presentation | bar: 2019-05-13
Miscellaneous
M1 | Create Git repository
M2 | Install LaTeX
M3 | Create Meeting Minutes Document
M4 | Plan 2nd stage of Project
M5 | Print and Collate Final Hand In | bar: 2019-04-08
M6 | SET/SEM Questionaries' | bar: 2019-05-13
Other Commitments
C1 | Welcome Weeks
C2 | Christmas Holiday
C3 | Autumn Exams
C4 | Easter Holiday | bar: 2019-04-15 to 2019-05-06